Building AI Agents for Procedures

Project Execution Plan

April 2025 – May 2025

# Project Overview

Construction workers often encounter unexpected events in the field requiring outside expertise. Team leaders are sometimes unavailable, and company-provided procedures are often verbose and difficult to navigate quickly. This project builds AI Agents trained on generic, wide-spanning procedures to reliably answer technician questions — reducing escalation delays and improving field decision-making.

## Objectives

- Build a functional AI agent trained on procedure documents that can answer nearly any relevant question.

- Create an evaluation framework to measure agent reliability and surface knowledge gaps.

- Produce video demonstrations and thorough documentation for training and handoff purposes.

- Deliver a risk assessment and cost-benefit analysis for organizational deployment.

## Key Deliverables

| Deliverable | Description |
| --- | --- |
| AI Agent | A working agent that answers questions about trained procedures |
| Q&A Gap Repository | A curated list of questions the agent cannot answer |
| Video Demos | Recorded sessions of agent interaction for training use |
| Risk & CBA Report | Risk assessment and cost-benefit analysis for companies |
| Documentation | Full docs covering creation, training, tuning, testing, updating |

# Overall Approach

The project follows a RAG (Retrieval-Augmented Generation) architecture. Procedures are loaded into a vector knowledge base, and the agent retrieves the most relevant chunks before generating a response. This grounds the agent's answers in real documents rather than hallucinated information.

## Architecture Summary

- Procedure documents (PDF/Markdown) are ingested and chunked into a vector store.

- User queries trigger semantic search against the vector store.

- The top-k relevant chunks are fed as context to the LLM (Claude API).

- The agent generates a grounded answer. If it cannot find relevant context, it flags the question as unanswered.

- All interactions are logged for reliability evaluation and gap analysis.

## Evaluation Strategy

Reliability is measured using a structured question set created by the team. Each question is scored on:

- Correctness: Does the answer match the ground truth from the procedure?

- Completeness: Does it cover all required steps or information?

- Hallucination rate: Does it fabricate information not in the source documents?

- Coverage: What percentage of questions can it answer vs. flag as unknown?

# Tech Stack

| Category | Technology | Purpose |
| --- | --- | --- |
| AI Platform | Claude AI (Anthropic) | Core LLM powering the agent's NLP capabilities |
| Agent Builder | Claude Projects / Dify / Flowise | No-code/low-code agent creation and RAG pipeline |
| Knowledge Base | PDF / Markdown Procedures | Source documents fed into the agent |
| Vector Store | ChromaDB / Pinecone | Embedding storage for semantic search |
| Embedding Model | Claude Embeddings / OpenAI | Convert procedure text to vector embeddings |
| Backend API | Python (FastAPI) | Wrapper API for agent queries and logging |
| Frontend | React.js / Streamlit | Chat UI for agent interaction & demonstration |
| Database | PostgreSQL / SQLite | Store Q&A logs, unanswered questions, metrics |
| Version Control | GitHub | Source control, collaboration, CI/CD pipelines |
| Evaluation | Python (pytest + custom scripts) | Automated reliability scoring and gap analysis |
| Recording | OBS Studio / Loom | Video demonstrations of agent interactions |
| Documentation | Markdown + Google Docs | Technical docs, training guides, reports |
| Deployment | Render / Railway / Hugging Face Spaces | Cloud hosting for the agent and UI |

# Project Timeline Overview

| Phase | Dates & Duration |
| --- | --- |
| Phase 1: Setup & Scoping | Week 1 (Apr 1–7) |
| Phase 2: Data Preparation | Week 2 (Apr 8–14) |
| Phase 3: Agent Building | Week 3–4 (Apr 15–28) |
| Phase 4: Evaluation & Tuning | Week 5 (Apr 29–May 5) |
| Phase 5: Documentation & Demos | Week 6 (May 6–19) |
| Phase 6: Final Review & Deployment | Week 7–8 (May 20–31) |

| Phase 1: Setup & Scoping | Apr 1–7 |
| --- | --- |

## Goal

Establish the project foundation: align on scope, configure tools, select procedures, and define the evaluation criteria before any building begins.

## Steps

### Step 1.1 — Team Kickoff & Role Assignment

- Hold a kickoff meeting to align on project goals, deliverables, and individual responsibilities.

- Assign roles: Agent Developer, Evaluation Lead, Documentation & Demo Lead.

- Set up a shared communication channel (e.g., Discord, Slack, or Teams).

- Establish a shared folder structure (Google Drive or GitHub repo) for all project assets.

### Step 1.2 — Procedure Selection

- Research and identify 3–5 publicly available, wide-spanning procedures suitable for construction or field work contexts (e.g., OSHA safety procedures, equipment shutdown procedures, emergency response protocols).

- Evaluate each for: length, clarity, digital availability (PDF/web), and question-generating potential.

- Finalize procedure selection and download/archive all source documents.

### Step 1.3 — Environment & Tool Setup

- Create a shared GitHub repository with a defined folder structure (data/, agent/, evaluation/, docs/, demo/).

- Set up a Python virtual environment. Install core dependencies: langchain, anthropic, chromadb, fastapi, pytest.

- Configure access to Claude API (obtain API keys, test connection).

- Set up the chosen agent builder (Claude Projects, Dify, or Flowise). Do a smoke-test with a simple document.

- Set up the database (SQLite for local dev, PostgreSQL for prod) and define the schema for logging Q&A interactions.

### Step 1.4 — Define Evaluation Criteria

- Draft the scoring rubric: Correctness (0–3), Completeness (0–3), Hallucination flag (yes/no), Answered/Unanswered classification.

- Create a template spreadsheet for manual evaluation.

- Define what constitutes a 'reliable' agent (e.g., >80% correctness score on the test set).

### Step 1.5 — Project Plan Finalization

- Review and finalize this project plan document.

- Confirm timeline, assign phase owners, and set weekly check-in schedule.

🏁 Milestone: Phase 1 Complete: Environment running, procedures selected, repo initialized, evaluation rubric finalized, roles confirmed.

| Phase 2: Data Preparation | Apr 8–14 |
| --- | --- |

## Goal

Transform raw procedure documents into a clean, structured knowledge base that the AI agent can effectively retrieve from.

## Steps

### Step 2.1 — Document Cleaning & Formatting

- Convert all procedures to a clean, consistent format (Markdown preferred, PDF acceptable).

- Remove headers/footers, page numbers, and formatting artifacts that don't add semantic value.

- Ensure all procedures are stored in the data/procedures/ directory with consistent naming conventions.

### Step 2.2 — Document Chunking Strategy

- Experiment with chunking strategies: fixed-size (500–1000 tokens), semantic chunking by section/heading, or sentence-based.

- Evaluate chunk overlap settings (recommended: 10–20% overlap to preserve context across boundaries).

- Document the chosen chunking strategy with rationale.

### Step 2.3 — Embedding & Vector Store Ingestion

- Write an ingestion script (ingest.py) that: loads documents, splits into chunks, generates embeddings, and stores in ChromaDB.

- Run ingestion for all procedures. Log the total number of chunks created per document.

- Test retrieval by running 5–10 manual queries to confirm relevant chunks are being returned.

### Step 2.4 — Ground Truth Question Set Creation

- For each procedure, write 15–20 test questions ranging from simple (fact lookup) to complex (multi-step reasoning).

- Write the correct expected answer for each question, referenced directly from the procedure text.

- Aim for at least 60 total Q&A pairs across all procedures.

- Store in evaluation/ground_truth.csv with columns: question, expected_answer, source_document, difficulty.

🏁 Milestone: Phase 2 Complete: All procedures cleaned and ingested into vector store. Ground truth Q&A set (60+ pairs) created and stored.

| Phase 3: Agent Building & Integration | Apr 15–28 |
| --- | --- |

## Goal

Build, configure, and integrate the AI agent — connecting the vector store, LLM, and interface layer into a working, testable system.

## Steps

### Step 3.1 — System Prompt Engineering

- Write the agent's system prompt defining its persona, task, and behavioral guardrails.

- Key elements to include: role (field procedure assistant), response format, instruction to cite source sections, behavior when answer is unknown (flag and log it, do not hallucinate).

- Iterate on the system prompt with 10–15 manual test queries. Refine until behavior is consistent.

### Step 3.2 — RAG Pipeline Construction

- Build the core RAG pipeline in agent/rag_pipeline.py:

- Accept a user query as input.

- Run semantic search against the vector store to retrieve top-k chunks.

- Construct a prompt with retrieved context + user query.

- Call Claude API and return the response.

- Log the query, retrieved chunks, response, and timestamp to the database.

- Test end-to-end with 20 queries from the ground truth set. Fix any pipeline errors.

### Step 3.3 — Unanswered Question Detection

- Implement logic to detect when the agent cannot find an answer in the knowledge base.

- When confidence is low or context is irrelevant, the agent should respond: 'I cannot find this information in the available procedures. This question has been logged for review.'

- Log all such queries to a separate table/CSV: evaluation/unanswered_questions.csv.

### Step 3.4 — Frontend Chat Interface

- Build a simple chat UI using Streamlit or React.js.

- Interface should display: chat history, source citations for each answer, and a flag indicator for unanswered questions.

- Connect the UI to the FastAPI backend (if applicable) or directly to the pipeline.

- Test the full user flow end-to-end.

### Step 3.5 — Internal Alpha Testing

- Run the full 60-question ground truth set through the agent.

- Log all responses. Identify obvious failure modes (wrong retrieval, bad prompting, hallucinations).

- Make targeted fixes based on findings (adjust chunk size, refine prompt, tune retrieval k).

🏁 Milestone: Phase 3 Complete: Working agent with RAG pipeline, chat UI, unanswered-question logging, and successful alpha test on ground truth set.

| Phase 4: Evaluation & Tuning | Apr 29–May 5 |
| --- | --- |

## Goal

Systematically evaluate agent reliability, measure against the defined metrics, identify gaps, and tune the agent until it meets the reliability threshold.

## Steps

### Step 4.1 — Automated Evaluation Script

- Write evaluation/evaluate.py that runs all 60+ ground truth questions through the agent and records responses.

- Score each response on: Correctness (0–3), Completeness (0–3), Hallucination (Y/N), Answered/Unanswered.

- Compute aggregate metrics: overall accuracy %, hallucination rate %, coverage %, average score.

- Output a results report to evaluation/results_report.csv.

### Step 4.2 — Manual Review of Borderline Cases

- Manually review all questions scored 1 or lower for Correctness.

- Diagnose root cause for each failure: retrieval failure, context window issue, prompt issue, or missing procedure content.

- Log each root cause in a findings table.

### Step 4.3 — Agent Tuning

- Based on evaluation findings, make targeted tuning adjustments:

- If retrieval fails: increase k, adjust chunk size, or try hybrid search.

- If hallucination occurs: tighten system prompt instructions, reduce temperature.

- If completeness is low: adjust chunk overlap, ensure full section retrieval.

- Re-run evaluation after each tuning cycle. Track scores across versions in a tuning log.

- Target: >80% correctness, <5% hallucination rate.

### Step 4.4 — Gap Repository Compilation

- Compile all questions the agent consistently fails to answer into evaluation/gap_repository.csv.

- Categorize gaps: missing procedure content, ambiguous question wording, retrieval limitations, or out-of-scope topics.

- This repository becomes a key deliverable and can be used to update procedures in the future.

🏁 Milestone: Phase 4 Complete: Evaluation report produced. Agent tuned to >80% correctness. Gap repository finalized with categorized unanswerable questions.

| Phase 5: Documentation & Video Demos | May 6–19 |
| --- | --- |

## Goal

Create comprehensive documentation and recorded demonstrations that enable future teams, stakeholders, or companies to understand, replicate, and train using this agent.

## Steps

### Step 5.1 — Technical Documentation

- Write docs/technical_guide.md covering:

- Architecture diagram and component descriptions.

- Setup instructions (environment, dependencies, API keys).

- Ingestion pipeline: how to add new procedures to the knowledge base.

- Running the agent locally and via the deployed URL.

- How to run the evaluation script and interpret results.

- Write docs/tuning_log.md summarizing all tuning iterations and their outcomes.

### Step 5.2 — Creation & Training Process Documentation

- Write a narrative document (docs/creation_process.md) explaining:

- Why each technology was chosen.

- How the agent was built step-by-step (decisions made, alternatives considered).

- Lessons learned and recommendations for replication.

- This document should be readable by a non-technical manager, not just developers.

### Step 5.3 — Risk Assessment & Cost-Benefit Analysis

- Write docs/risk_cba_report.md covering:

- Risks: data privacy (procedure confidentiality), hallucination liability, over-reliance by field workers, technical failure in low-connectivity environments.

- Mitigations for each identified risk.

- Cost side: development hours, API costs, hosting, maintenance.

- Benefit side: time saved per escalation, reduced manager interruptions, faster decision-making.

- Overall CBA recommendation: go/no-go for organizational deployment.

### Step 5.4 — Video Demonstrations

- Record 2–3 demonstration videos using OBS Studio or Loom:

- Demo 1: Basic agent interaction — ask 5 questions, show correct answers with citations.

- Demo 2: Edge case handling — show how the agent responds to ambiguous and unanswerable questions.

- Demo 3: Walkthrough of the evaluation results and gap repository for a non-technical audience.

- Videos should be 3–7 minutes each. Upload to a shared Google Drive folder.

- Each team member should appear in at least one video.

🏁 Milestone: Phase 5 Complete: Technical docs, creation process docs, risk/CBA report, and 3 demo videos all finalized and stored.

| Phase 6: Final Review & Deployment | May 20–31 |
| --- | --- |

## Goal

Deploy the agent to a publicly accessible URL, conduct a final review of all deliverables, and prepare the project for submission.

## Steps

### Step 6.1 — Deployment

- Deploy the backend (FastAPI) and frontend (Streamlit/React) to a cloud platform (Render, Railway, or Hugging Face Spaces).

- Ensure the vector store is persisted (not ephemeral) so the agent retains its knowledge base after restarts.

- Test the deployed version with 10 queries to confirm it works identically to the local version.

- Document the deployment URL and access instructions in the README.

### Step 6.2 — Full Deliverable Review

- Each team member reviews the complete set of deliverables against the project brief checklist.

- Verify: agent works, gap repo is complete, videos are uploaded, all docs are finalized, risk report is done.

- Fix any remaining gaps or incomplete sections.

### Step 6.3 — Final Evaluation Run

- Run one final evaluation pass on the deployed agent (not local) using the full ground truth set.

- Record the final metrics: correctness %, hallucination rate, coverage %. These are the official project metrics.

- Add a Final Results section to the evaluation report.

### Step 6.4 — README & Submission Package

- Write a comprehensive README.md at the root of the GitHub repo:

- Project summary (2–3 sentences).

- Live demo URL.

- Setup instructions.

- Links to all documentation, video demos, evaluation report, and gap repository.

- Team member names and roles.

- Create a final submission ZIP or share the GitHub repo link as the submission artifact.

### Step 6.5 — Retrospective

- Hold a final team retrospective meeting.

- Document 3 things that went well, 3 things to improve, and 3 recommendations for future teams.

- Add this to docs/retrospective.md.

🏁 Milestone: Phase 6 Complete: Agent deployed to production URL. All deliverables reviewed and finalized. Submission package ready. Project complete by May 31.

# Risk Register

| Risk | Mitigation |
| --- | --- |
| API rate limits or cost overruns | Set daily API spend limits. Use caching for repeated queries during evaluation. |
| Procedures too short / low information density | Select multiple procedures to ensure broad coverage. Augment with related public documents. |
| Agent hallucinations in demos | Tune temperature, add strict grounding instructions. Rehearse demo questions in advance. |
| Team member unavailability | Maintain shared documentation so any member can pick up another's work. |
| Deployment platform issues | Test deployment early (end of Phase 3). Have a backup platform identified. |
| Evaluation score below threshold | Build tuning buffer time into Phase 4. Reduce scope of procedures if needed. |

# Repository Folder Structure

| Folder / File | Contents |
| --- | --- |
| data/procedures/ | Source procedure documents (PDF/Markdown) |
| data/chunks/ | Processed text chunks (optional export) |
| agent/ingest.py | Document ingestion and embedding script |
| agent/rag_pipeline.py | Core RAG pipeline (query → retrieval → response) |
| agent/system_prompt.txt | Agent system prompt (versioned) |
| api/main.py | FastAPI backend |
| frontend/ | Streamlit or React chat interface |
| evaluation/ground_truth.csv | 60+ ground truth Q&A pairs |
| evaluation/evaluate.py | Automated evaluation script |
| evaluation/results_report.csv | Per-run evaluation scores |
| evaluation/gap_repository.csv | Unanswerable / gap questions |
| docs/technical_guide.md | Full technical documentation |
| docs/creation_process.md | Narrative creation & training doc |
| docs/risk_cba_report.md | Risk assessment & cost-benefit analysis |
| docs/tuning_log.md | Agent tuning iteration log |
| docs/retrospective.md | Team retrospective notes |
| demos/ | Video demo files or links |
| README.md | Project overview and submission links |